## 01_Product_Modules
Module Code | Module Name AR | Module Name EN | MVP/Phase2 | Depends On | Notes
auth | الدخول والصلاحيات | Auth | MVP | - | Phase 0 implemented (schema only)
organizations | الشركات | Organizations | MVP | auth | Phase 0 implemented (schema only)
users | المستخدمون | Users | MVP | auth | Phase 0 implemented (schema only)
permissions | الصلاحيات | Permissions | MVP | auth,users | Phase 0 implemented (schema only)
accounting | المحاسبة | Accounting | MVP | organizations | Phase 0: Posting Engine + tests implemented
sales | المبيعات | Sales | MVP | accounting,tax | Simple Mode implemented and live-tested — Canonical Invoice Model still pending
purchases | المشتريات | Purchases | MVP | accounting,inventory | Simple Mode (Bill) implemented and live-tested
expenses | المصروفات | Expenses | MVP | accounting | Implemented and live-tested
inventory | المخزون | Inventory | MVP | accounting | Weighted Average costing implemented and live-tested — multi-warehouse/variants/serials/lots pending
pos | نقطة البيع | POS | MVP | sales,inventory,tax,accounting,zatca | Sell + Return implemented and live-tested — Shift/Hold-Resume/hardware pending
banking | البنوك والخزينة | Banking | MVP | accounting | Transfer implemented and live-tested — reconciliation not started
projects | المشاريع | Projects | Phase2 | accounting | Not started
contracting | المقاولات | Contracting | Phase2 | projects | Not started
agriculture | الزراعة | Agriculture | Phase2 | inventory | Not started
assets | الأصول الثابتة | Fixed Assets | MVP | accounting | Acquisition + straight-line depreciation implemented and live-tested
tax | الضرائب | Tax Engine | MVP | accounting | Not started
invoice-studio | استوديو الفواتير | Invoice Studio | MVP | sales,tax | Not started — but see 'zatca' row: a real UBL 2.1 XML generator now exists as a first building block
zatca | الفوترة الإلكترونية | ZATCA | MVP | invoice-studio | Phase 1 QR: implemented and verified. Phase 2: real UBL 2.1 XML generator implemented (Sprint 30), built directly from the official spec and live-tested against real transaction data — still missing cryptographic stamp, real CSID, and a persistent invoice-number ledger, all of which require actual ZATCA onboarding credentials this build has never had
reports | التقارير | Reports | MVP | accounting,inventory,pos | Not started
notifications | الإشعارات | Notifications | Phase2 | - | Not started
audit | سجل التدقيق | Audit | MVP | auth | Not started
subscriptions | الاشتراكات | Subscriptions | Phase2 | organizations | Not started

## 02_Business_Sectors
sector_code | الاسم بالعربي | Name EN
RETAIL | التجزئة | Retail
WHOLESALE | الجملة | Wholesale
SERVICES | الخدمات | Services
CONTRACTING | المقاولات | Contracting
AGRICULTURE | الزراعة | Agriculture
TOURISM | السياحة | Tourism
PROFESSIONAL_OFFICES | المكاتب المهنية | Professional Offices

## 03_Business_Activities
activity_code | sector_code | الاسم بالعربي | Name EN
SUPERMARKET | RETAIL | سوبر ماركت / بقالة | Grocery / Mini Market
CLOTHING | RETAIL | ملابس | Clothing
SHOES | RETAIL | أحذية | Shoes
PERFUMES | RETAIL | عطور | Perfumes
ELECTRONICS | RETAIL | إلكترونيات | Electronics
MOBILE | RETAIL | جوالات | Mobile
AUTO_PARTS | RETAIL | قطع غيار سيارات | Auto Parts
STATIONERY | RETAIL | قرطاسية | Stationery
HOME_SUPPLIES | RETAIL | مستلزمات منزلية | Home Supplies
BUILDING_MATERIALS | RETAIL | مواد بناء | Building Materials
GENERAL_TRADING | WHOLESALE | تجارة عامة | General Trading
DISTRIBUTION | WHOLESALE | توزيع | Distribution
IMPORT_EXPORT | WHOLESALE | استيراد وتصدير | Import/Export
IT_SERVICES | SERVICES | خدمات تقنية | IT Services
MAINTENANCE | SERVICES | صيانة | Maintenance
CONSULTING | SERVICES | استشارات | Consulting
MARKETING | SERVICES | تسويق | Marketing
TRAINING | SERVICES | تدريب | Training
ELECTRICAL_CONTRACTING | CONTRACTING | مقاولات كهربائية | Electrical Contracting
MECHANICAL_CONTRACTING | CONTRACTING | مقاولات ميكانيكية | Mechanical Contracting
FIT_OUT | CONTRACTING | تشطيبات | Fit-Out
OPERATIONS_MAINTENANCE | CONTRACTING | تشغيل وصيانة | Operations & Maintenance
FARMING | AGRICULTURE | زراعة | Farming
AGRI_SUPPLIES | AGRICULTURE | مستلزمات زراعية | Agricultural Supplies
PRODUCE_DISTRIBUTION | AGRICULTURE | توزيع منتجات زراعية | Produce Distribution
HAJJ_UMRAH | TOURISM | الحج والعمرة | Hajj & Umrah
TRIPS_TRANSPORT | TOURISM | رحلات ونقل | Trips & Transportation
ACCOUNTING_OFFICE | PROFESSIONAL_OFFICES | مكتب محاسبة | Accounting Office
ENGINEERING_OFFICE | PROFESSIONAL_OFFICES | مكتب هندسي | Engineering Office
LEGAL_OFFICE | PROFESSIONAL_OFFICES | مكتب قانوني | Legal Office

## 04_Feature_Packs
Pack | sector_code | Default Modules Added | Invoice Templates | Special Behavior
Retail Pack | RETAIL | pos, inventory(variants+barcode) | Retail A4, Retail Thermal 80mm | Barcode, variants, walk-in customer default
Wholesale Pack | WHOLESALE | sales(quotation→SO), purchases | Corporate Professional | Credit limits, aging emphasis
Services Pack | SERVICES | projects(light) | Services | Period/hours billing, no physical inventory
Contracting Pack | CONTRACTING | projects, contracting(BOQ, retention) | Contracting | Progress Certificate ≠ Tax Invoice workflow
Agriculture Pack | AGRICULTURE | inventory(lots/batches, weight units) | Agriculture | Gross/tare/net weight, harvest date, grading
Tourism Pack | TOURISM | sales(packages) | Services | Trip/package line items
Accounting Office Pack | PROFESSIONAL_OFFICES | multi-client architecture (Phase2) | Minimal | One firm managing several client tenants

## 05_Chart_of_Accounts
Code | الاسم بالعربي | Name EN | Type | Parent | Posting/Header
1000 | الأصول | Assets | ASSET | - | Header
1100 | النقدية | Cash | ASSET | 1000 | Posting
1110 | البنك | Bank | ASSET | 1000 | Posting
1120 | حساب تسوية البطاقات | Card Clearing Account | ASSET | 1000 | Posting
1200 | العملاء | Accounts Receivable | ASSET | 1000 | Posting
1300 | المخزون | Inventory | ASSET | 1000 | Posting
1400 | ضريبة القيمة المضافة - مدخلات | VAT Input | ASSET | 1000 | Posting
1500 | الأصول الثابتة | Fixed Assets | ASSET | 1000 | Posting
1510 | مجمّع الإهلاك | Accumulated Depreciation | ASSET | 1000 | Posting
2000 | الالتزامات | Liabilities | LIABILITY | - | Header
2100 | الموردون | Accounts Payable | LIABILITY | 2000 | Posting
2200 | ضريبة القيمة المضافة - مخرجات | VAT Output | LIABILITY | 2000 | Posting
3000 | حقوق الملكية | Equity | EQUITY | - | Header
3100 | رصيد افتتاحي | Opening Balance Equity | EQUITY | 3000 | Posting
4000 | الإيرادات | Revenue | REVENUE | - | Header
4100 | المبيعات | Sales | REVENUE | 4000 | Posting
4200 | مردودات المبيعات | Sales Returns | REVENUE | 4000 | Posting
5000 | تكلفة المبيعات | Cost of Sales | COST_OF_SALES | - | Header
5100 | تكلفة البضاعة المباعة | COGS | COST_OF_SALES | 5000 | Posting
6000 | المصروفات التشغيلية | Operating Expenses | EXPENSE | - | Header
6100 | مصروفات عامة | General Expense | EXPENSE | 6000 | Posting
6200 | مصروف الإهلاك | Depreciation Expense | EXPENSE | 6000 | Posting

## 06_Accounting_Posting_Matrix
Event | Source Document | Debit | Credit | VAT Effect | Inventory Effect | COGS | Reversal Method
SALE_INVOICE_POSTED | Sales Invoice | Accounts Receivable | Sales + VAT Output | VAT Output + | Issue | Yes (COGS Dr / Inventory Cr) | Credit Note
POS_SALE_COMPLETED (Cash) | POS Sale | Cash | Sales + VAT Output | VAT Output + | Issue | Yes | POS Return
POS_SALE_COMPLETED (Card) | POS Sale | Card Clearing Account | Sales + VAT Output | VAT Output + | Issue | Yes | POS Return
POS_SALE_COMPLETED (Mixed) | POS Sale | Cash + Card Clearing (split) | Sales + VAT Output | VAT Output + | Issue | Yes | POS Return
POS_RETURN_COMPLETED | POS Return | Sales Returns + VAT Output | Cash/Card Clearing | VAT Output − | Return | Reverse COGS | N/A (already a reversal doc)
PURCHASE_BILL_POSTED | Supplier Bill | Inventory + VAT Input | Accounts Payable | VAT Input + | Receive | No | Purchase Return
PURCHASE_RETURN_COMPLETED | Purchase Return | Accounts Payable | Inventory + VAT Input | VAT Input − | Issue (out) | No | N/A
EXPENSE_POSTED | Expense | Expense Account + VAT Input | Cash/Bank/Payable | VAT Input + (if applicable) | None | No | Manual Reversal
PAYMENT_RECEIVED | Customer Payment | Cash/Bank | Accounts Receivable | None | None | No | Manual Reversal
PAYMENT_PAID | Supplier Payment | Accounts Payable | Cash/Bank | None | None | No | Manual Reversal
INVENTORY_RECEIVED | Goods Receipt / Opening Balance | Inventory | Opening Balance Equity / GRNI | None | Receive | No | Adjustment
STOCK_ADJUSTED | Inventory Count / Damage | Inventory (or Expense if loss) | Inventory Adjustment / Inventory | None | Adjust | Depends | Reverse Adjustment
ASSET_ACQUIRED | Asset Purchase | Fixed Asset | Cash/Bank/Payable | VAT Input + (if applicable) | None | No | Manual Reversal
ASSET_DEPRECIATED | Periodic Depreciation | Depreciation Expense | Accumulated Depreciation | None | None | No | Reverse Entry
MANUAL_JOURNAL_POSTED | Manual Journal | As specified | As specified | As specified | None | No | Reversal Journal

## 07_Database_Tables
Table Name | Purpose | Tenant Scope | Financial Criticality | Audit Requirement | Status
organizations | Root tenant record | N/A (is the tenant) | High | Yes | Implemented (Prisma)
branches | Branch/location per org | organization_id | Medium | Yes | Implemented (Prisma)
users | Login identity, global | N/A | Low | Yes | Implemented (Prisma)
organization_users | User↔Org↔Role membership | organization_id | Medium | Yes | Implemented (Prisma)
roles | Tenant-scoped role | organization_id | Medium | Yes | Implemented (Prisma)
permissions | Global permission catalog | N/A | Low | No | Implemented (Prisma)
role_permissions | Role↔Permission grant | via role.organization_id | Medium | Yes | Implemented (Prisma)
accounts | Chart of Accounts (tree) | organization_id | Critical | Yes | Implemented (Prisma)
fiscal_years | Year boundary + status | organization_id | Critical | Yes | Implemented (Prisma)
accounting_periods | Period boundary + status | via fiscal_year.organization_id | Critical | Yes | Implemented (Prisma)
journal_entries | Posted accounting entry header | organization_id | Critical | Yes | Implemented (Prisma)
journal_entry_lines | Debit/credit lines | via journal_entry.organization_id | Critical | Yes | Implemented (Prisma)
customers / suppliers | Parties | organization_id | High | Yes | Not started
products / product_variants | Catalog | organization_id | High | Yes | Not started
warehouses / inventory_movements | Stock ledger | organization_id | Critical | Yes | Not started
invoice_documents ... invoice_render_versions | Canonical Invoice domain (see band 61) | organization_id | Critical | Yes | Not started
pos_terminals / pos_shifts / pos_sales | POS domain | organization_id / branch_id | Critical | Yes | Not started
zatca_documents / zatca_submissions / zatca_submission_attempts | ZATCA integration log | organization_id | Critical | Yes | Not started — blocked on source verification

## 08_ERD_Reference
Relationship | Notes
organizations 1─* branches | Every branch belongs to exactly one org
organizations 1─* organization_users ─* users | Many-to-many via join table; role lives on the join row
organizations 1─* roles ─* role_permissions ─* permissions | Roles are tenant-scoped; permissions are global
organizations 1─* accounts (self-referencing tree) | parent_id nullable, header accounts are non-postable
organizations 1─* fiscal_years 1─* accounting_periods | Periods cannot outlive their fiscal year's date range
organizations 1─* journal_entries 1─* journal_entry_lines ─* accounts | Only AccountingPostingEngine writes here
(future) invoice_documents 1─* zatca_documents 1─* zatca_submissions | Not modeled yet — see 07_Database_Tables

## 09_Invoice_Types
Invoice Type | ZATCA Classification | Model | Notes
Standard Tax Invoice (B2B/B2G) | Standard Tax Invoice | Clearance | Buyer VAT number required if buyer registered
Simplified Tax Invoice (B2C) | Simplified Tax Invoice | Reporting (within 24h) | QR code mandatory on print/share
Credit Note | Associated to original invoice type | Follows original's model | Must reference original invoice UUID
Debit Note | Associated to original invoice type | Follows original's model | Must reference original invoice UUID
Progress Certificate (Contracting) | NOT a ZATCA tax document itself | N/A | Business template only — see band 48/82; the resulting Tax Invoice is what's classified

## 10_Invoice_Fields
Field Group | Fields | Classification
Seller | Legal name, VAT number, CR number, National Address | ZATCA_REQUIRED
Buyer | Name, VAT number (if B2B), address | ZATCA_CONDITIONAL
Invoice Meta | Number, UUID, issue date/time, invoice type code | ZATCA_REQUIRED
Lines | Description, quantity, unit, unit price, discount, VAT category, line total | ZATCA_REQUIRED
Totals | Subtotal, discount total, VAT total, grand total | ZATCA_REQUIRED
Security | QR code, cryptographic stamp, hash, previous invoice hash (Phase 2) | ZATCA_REQUIRED
Branding (business-optional) | Logo, header/footer text, color, watermark, signature image | BUSINESS_OPTIONAL

## 11_Invoice_Templates
Template | Page Size | Language | Status
Classic Arabic | A4 | AR | Design pending
Modern Arabic | A4 | AR | Design pending
Corporate Professional | A4 | AR/EN | Design pending
Arabic-English Bilingual | A4 | AR+EN | Design pending
Minimal | A4 | AR/EN | Design pending
Retail A4 | A4 | AR | Design pending
Retail Thermal 80mm | 80mm | AR | Design pending
Services | A4 | AR/EN | Design pending
Contracting | A4 | AR/EN | Design pending
Agriculture | A4 | AR | Design pending

## 12_Template_Field_Rules
Classification | Meaning | User Can Hide? | User Can Move/Restyle?
BUSINESS_OPTIONAL | Nice-to-have business info | Yes | Yes
BUSINESS_REQUIRED | Required by this business's own policy | No (org admin only) | Yes
ZATCA_REQUIRED | Mandated by ZATCA on every applicable invoice | No | Position/style only, never hidden
ZATCA_CONDITIONAL | Mandated only in certain cases (e.g. buyer VAT for B2B) | No, when condition applies | Position/style only
XML_ONLY | Present in XML but not necessarily printed | N/A — not a print field | N/A
DISPLAY_REQUIRED | Must be human-readable on the printed/shared copy | No | Position/style only

## 13_ZATCA_Field_Mapping
Internal Field | Official BT/KSA ID | Business Rule(s) | Required/Conditional | Applicable Invoice Type | Source
invoice.uuid | KSA-1 | BR-KSA-03: unique UUID generated by the issuing system, letters/digits/dashes only | Required | All | XML Standard v1.2 §13.3.1
invoice.number | BT-1 | BR-02: every invoice must have a number | Required | All | XML Standard v1.2 §13.2.1
invoice.issueDate | BT-2 | BR-03 / BR-KSA-04: must be <= current date | Required | All | XML Standard v1.2
invoice.issueTime | KSA-25 | BR-KSA-70: format hh:mm:ss (local) or hh:mm:ssZ (UTC) | Required | All | XML Standard v1.2 §13.3.1
invoice.typeCode | BT-3 | 388=Tax Invoice, 383=Debit Note, 381=Credit Note, 386=Prepayment Invoice | Required | All | XML Standard v1.2 §11.2.1
invoice.subtype | KSA-2 | 7-char flag string: subtype(01/02) + 3rd-party + nominal + export + summary + self-billed | Required | All | XML Standard v1.2 §11.2.1 / BR-KSA-06
seller.name | BT-27 | BR-06: seller legal registration name | Required | All | XML Standard v1.2
seller.vatNumber | BT-31 | BR-KSA-39/40: 15 digits, first and last digit = 3 | Required | All | XML Standard v1.2 §13.3.1
seller.address | BG-5 (street/building/postal/city/district/country) | BR-08/09, BR-KSA-09: full national-address components required | Required | All | XML Standard v1.2
buyer.name | BT-44 | BR-KSA-42: required on Tax Invoice; BR-KSA-25/71: required in specific Simplified cases | Conditional | Mainly Standard | XML Standard v1.2
buyer.vatNumber | BT-48 | BR-KSA-44: 15 digits, first/last = 3; not required for exports (BR-KSA-46) | Conditional (B2B) | Standard | XML Standard v1.2
buyer.otherId | BT-46 | BR-KSA-14/81: required if buyer has no VAT number, one of TIN/CRN/MOM/MLS/700/SAG/NAT/GCC/IQA/PAS/OTH | Conditional | Standard | XML Standard v1.2 §13.3.1
invoiceLine.vatCategory | BT-151 | One of S/Z/E/O — drives BR-S/BR-Z/BR-E/BR-O rule sets | Required | All | XML Standard v1.2 §11.2.4
invoice.taxTotal | BT-110 | BR-CO-14: sum of all VAT category tax amounts (BT-117) | Required | All | XML Standard v1.2 §9.2
invoice.totalWithVat | BT-112 | BR-CO-15: total without VAT + total VAT | Required | All | XML Standard v1.2 §9.2
invoice.payableAmount | BT-115 | BR-CO-16: total with VAT − prepaid + rounding | Required | All | XML Standard v1.2 §9.2
invoice.previousInvoiceHash | KSA-13 | BR-KSA-26/61: Base64 SHA-256 of prior invoice; genesis value is the hash of "0" | Required (Phase 2) | All | Security Features v1.2 §3 + BR-KSA-26
invoice.qr | KSA-14 | BR-KSA-27: Base64, TLV-encoded, ≤700 chars — see sheet 15 for tag layout | Required | All (Simplified always; Standard human-readable copy) | Security Features v1.2 §4
invoice.cryptographicStamp | KSA-15 | BR-KSA-28/29/30: XAdES enveloped signature, fixed signature/reference IDs | Required (Phase 2) | All | Security Features v1.2 §2.3
invoice.counterValue | KSA-16 | BR-KSA-33/34: sequential, digits only, per EGS device | Required | All | XML Standard v1.2 §13.3.1

## 14_ZATCA_XML_Mapping
Concern | Verified Content | Source
Base standards | UBL 2.1 (main invoice schema) + ISO/CEN EN 16931:2017 + KSA-specific rules (BR-KSA*) layered on top; KSA rules override EN 16931 which overrides plain UBL on conflict | XML Standard v1.2 §1.3, §4
Validation phases | 1) XML well-formedness + UBL 2.1 schema; 2) content validation against EN 16931 subset + KSA (CIUS) country-qualified rules triggered by seller country = SA | XML Standard v1.2 §4
Rounding | Half-up rounding; round only the final result, never intermediate values; VAT category tax amount rounded at document level, not summed from rounded line VATs | XML Standard v1.2 §10
Invoice type codes | 388=Tax Invoice (388+"01"=standard, 388+"02"=simplified), 386=Prepayment Invoice, 383=Debit Note, 381=Credit Note | XML Standard v1.2 §11.2.1
Currency rule | Invoice totals may be in any currency; the tax total (BT-110/BT-111) must be expressed in SAR | XML Standard v1.2 §9.1, BR-KSA-EN16931-02
VAT calc formula | VAT category taxable amount = Σ(line net amounts) + document charges − document allowances, grouped by (category, rate); tax amount = taxable amount × rate/100 | XML Standard v1.2 §9.6
Rule families present | BR (integrity), BR-CO (conditions), BR-S/Z/E/O (per VAT category), BR-CL (code lists), BR-DEC (decimal precision), BR-KSA / BR-KSA-DEC / BR-KSA-CL / BR-KSA-EN16931 / BR-KSA-F (Saudi-specific) | XML Standard v1.2 §13
Not yet extracted | Full field-by-field Data Dictionary (names, definitions, character limits, examples) — lives in the companion XLSX, not the PDF; see ZATCA_SOURCES.md §2 for pending status | Data Dictionary (xlsx) — link recorded, content not yet parsed

## 15_ZATCA_QR_Mapping
Tag | Field | Phase / Enforcement date | Notes
1 | Seller's name | Phase 1 — 4 Dec 2021 | UTF-8 string, TLV length-prefixed
2 | Seller VAT registration number | Phase 1 — 4 Dec 2021 | 15-digit string
3 | Invoice timestamp (ISO 8601) | Phase 1 — 4 Dec 2021 | Example format: 2022-02-21T12:13:57Z
4 | Invoice total with VAT | Phase 1 — 4 Dec 2021 | Decimal as string
5 | VAT total (BT-110) | Phase 1 — 4 Dec 2021 | Decimal as string
6 | Hash of the XML invoice | Phase 2 — 1 Jan 2023 | SHA-256, 32 raw bytes (not hex/base64 inside the TLV value itself)
7 | ECDSA signature of the XML hash | Phase 2 — 1 Jan 2023 | Raw signature bytes
8 | ECDSA public key (from signing private key) | Phase 2 — 1 Jan 2023 | Raw public key bytes
9 | ZATCA's signature of the cryptographic stamp | Phase 2 — 1 Jan 2023 | Simplified Tax Invoices and their notes only

## 16_ZATCA_Security
Component | Verified Specification | Source
Hashing algorithm | SHA-256 | Security Features v1.2 §2.2.1 req. 16
Signature algorithm | ECDSA, key length 256 (P-256 curve) | Security Features v1.2 §2.2.1 req. 16, §2.2.2
Certificate standard | X.509 v3 per RFC 5280; validity up to 60 months from issuance | Security Features v1.2 §2.2.2
CSR subject fields (RDNs) | Common Name (device asset tag), Organization Identifier (15-digit VAT, first/last digit 3), Organization Unit (branch name, or 10-digit TIN for VAT-group members), Organization Name, Country, Invoice Type support flags (TSCZ bitmap), Location, Industry | Security Features v1.2 §2.2.2 Table 1
Onboarding flow | Taxpayer logs into taxpayer portal → submits CSR → ZATCA's technical CA validates and issues a Cryptographic Stamp Identifier (digital certificate) → certificate installed on the EGS | Security Features v1.2 §2.1.1
Certificate revocation check | CRL valid for 7 days (EGS may work offline up to 7 days before refreshing); OCSP also supported | Security Features v1.2 §2.2.1 req. 14
XML signature format | XAdES, enveloped, level B-B, per ETSI EN 319 132-1; the QR-code element itself is excluded from what gets signed via an XPath transform | Security Features v1.2 §2.2.1 req. 10-12, §2.3.3
PDF/A-3 signature format | PAdES per ETSI EN 319 142-1, when invoices are shared as PDF/A-3 with embedded XML | Security Features v1.2 §2.2.1 req. 10
EGS API authentication | OAuth 2.0 Basic Authentication — Client ID = the issued digital certificate, Secret = value issued at onboarding | Security Features v1.2 §5
Previous Invoice Hash (PIH) | Base64 SHA-256 of the previous invoice, computed the same way as the cryptographic stamp hash; the very first invoice uses the fixed genesis hash of the character "0" | Security Features v1.2 §3 + XML Standard BR-KSA-26

## 17_Tax_Codes
Tax Code | Rate | Category
STANDARD | 15% | Standard Rated
ZERO | 0% | Zero Rated
EXEMPT | N/A | Exempt
OUT_OF_SCOPE | N/A | Out of Scope

## 18_POS_Transactions
Transaction Type | Notes
Cash Sale | Single tender, full amount in cash
Card / Mada Sale | Posts to Card Clearing Account, not directly to Bank
Mixed Payment | Multiple tenders recorded separately (e.g. Cash 100 + Card 150)
Hold / Resume | Not a financial transaction — cart state only
Full Return | References original receipt; reverses inventory + accounting + VAT + ZATCA effect
Partial Return | Same as Full Return, scoped to selected lines/quantities
Shift Open / Close | Not a sale — records opening/expected/actual cash and variance

## 19_Inventory_Transactions
Movement Type | Accounting Effect
Opening Balance | Dr Inventory / Cr Opening Balance Equity
Purchase Receipt | Dr Inventory / Cr Accounts Payable (via PURCHASE_BILL_POSTED)
Sales Issue | Dr COGS / Cr Inventory (alongside the sale's revenue entry)
Sales Return | Dr Inventory / Cr COGS (reverse of Sales Issue)
Purchase Return | Dr Accounts Payable / Cr Inventory
Warehouse Transfer | No accounting effect — quantity moves between warehouses only
Adjustment | Dr/Cr Inventory vs Inventory Adjustment or Expense, depending on gain/loss
Damage/Loss | Dr Expense (or Inventory Write-off) / Cr Inventory

## 20_Contracting_Fields
Field | Notes
Project Name / Code | -
Contract Number | -
BOQ Item / Description / Unit | -
Contract Qty / Previous Qty / Current Qty / Accumulated Qty | -
Unit Rate / Current Value / Previous Value / Accumulated Value | -
Retention % / Retention Amount | -
Advance Recovery / Deductions | -
VAT / Net Amount | Computed by the same Invoice Calculation Engine as every other template

## 21_Agriculture_Fields
Field | Notes
Farm / Farm Location | -
Crop / Variety / Grade | -
Lot/Batch / Harvest Date | -
Gross Weight / Tare Weight / Net Weight | -
Quantity / Unit / Price per Unit / Price per KG-Ton | -
Packaging / Transport / Other Charges | -
Discount / Tax / Total | -

## 22_Roles
Role | Typical Scope
Owner | Full access across the organization
General Manager | Full operational access, org-wide
Finance Manager | Accounting, banking, reports, period closing
Chief Accountant | Journal posting/reversal, COA management
Accountant | Journal entry, invoices, payments (no reversal)
Branch Manager | Full access scoped to one branch
Sales | Sales invoices, customers
Purchasing | Purchase orders/bills, suppliers
Inventory Manager | Products, warehouses, adjustments
POS Supervisor | Discount overrides, shift approvals
Cashier | POS sales only, own shift
Auditor | Read-only + audit trail visibility
Read Only | View-only, no financial actions

## 23_Permissions
Permission Code | Module
invoice.view | invoice
invoice.create | invoice
invoice.approve | invoice
invoice.post | invoice
invoice.credit | invoice
invoice.print | invoice
invoice_template.view | invoice-studio
invoice_template.edit | invoice-studio
invoice_template.publish | invoice-studio
journal.create | accounting
journal.post | accounting
journal.reverse | accounting
pos.sell | pos
pos.return | pos
pos.discount | pos
pos.overrideDiscount | pos
pos.changePrice | pos
pos.cashIn | pos
pos.cashOut | pos
bank.reconcile | banking
reports.pnl.view | reports
zatca.view | zatca
zatca.manage | zatca
users.manage | users
settings.manage | organizations

## 24_Report_Catalog
Report | Category | Status
General Ledger | Financial | Implemented and live-tested (running balance per account)
Trial Balance | Financial | Implemented and live-tested
Profit & Loss | Financial | Implemented and live-tested
Balance Sheet | Financial | Implemented and live-tested — balance identity mathematically proven in tests
Cash Flow | Financial | Implemented and live-tested — direct method, Cash+Bank combined pool, bank transfers self-cancel
VAT Report | Financial | Not started
Customer Statement | Financial | Not started
Supplier Statement | Financial | Not started
Receivable Aging | Financial | Implemented and live-tested — buckets by age, excludes fully-paid invoices
Payable Aging | Financial | Implemented and live-tested — mirrors Receivable Aging logic
Stock Balance | Inventory | Covered by GET /inventory/products/:id/stock (not a dedicated report yet)
Inventory Valuation | Inventory | Not started
Low Stock | Inventory | Not started
Product Profitability | Inventory | Not started
Daily Sales | POS | Not started
Cashier Sales | POS | Not started
Shift Closing | POS | Not started — POS Shift itself not built yet
Project Profitability | Projects | Not started

## 25_API_Endpoints
Endpoint | Status
POST /api/v1/auth/login | Implemented and live-tested
POST /api/v1/organizations | Implemented and live-tested
POST /api/v1/organizations/:id/branches | Implemented and live-tested
GET /api/v1/organizations/:id/branches | Implemented and live-tested
POST /api/v1/organizations/:id/customers | Implemented and live-tested
POST /api/v1/organizations/:id/sales/invoices | Implemented and live-tested
POST /api/v1/organizations/:id/suppliers | Implemented and live-tested
POST /api/v1/organizations/:id/purchases/bills | Implemented and live-tested
POST /api/v1/organizations/:id/products | Implemented and live-tested
POST /api/v1/organizations/:id/inventory/receipts | Implemented and live-tested
POST /api/v1/organizations/:id/inventory/issues | Implemented and live-tested
GET /api/v1/organizations/:id/inventory/products/:productId/stock | Implemented and live-tested
POST /api/v1/organizations/:id/pos/sales | Implemented and live-tested
POST /api/v1/organizations/:id/pos/sales/:saleId/return | Implemented and live-tested
POST /api/v1/organizations/:id/accounting/journal-entries | Implemented and live-tested
POST /api/v1/organizations/:id/accounting/journal-entries/:id/reverse | Implemented and live-tested
GET /api/v1/organizations/:id/accounting/periods/:id/trial-balance | Implemented and live-tested
GET /api/v1/organizations/:id/reports/periods/:id/general-ledger | Implemented and live-tested
GET /api/v1/organizations/:id/reports/periods/:id/profit-and-loss | Implemented and live-tested
GET /api/v1/organizations/:id/reports/periods/:id/balance-sheet | Implemented and live-tested
GET /api/v1/organizations/:id/reports/periods/:id/cash-flow | Implemented and live-tested
POST /api/v1/organizations/:id/expenses | Implemented and live-tested
POST /api/v1/organizations/:id/assets | Implemented and live-tested
POST /api/v1/organizations/:id/assets/:id/depreciate | Implemented and live-tested
POST /api/v1/organizations/:id/banking/transfers | Implemented and live-tested
POST /api/v1/organizations/:id/pos/sales/:id/return-items | Implemented and live-tested
POST /api/v1/organizations/:id/payments/customer | Implemented and live-tested
POST /api/v1/organizations/:id/payments/supplier | Implemented and live-tested
GET /api/v1/organizations/:id/statements/customer/:id | Implemented and live-tested
GET /api/v1/organizations/:id/statements/supplier/:id | Implemented and live-tested
GET /api/v1/organizations/:id/aging/receivable | Implemented and live-tested
GET /api/v1/organizations/:id/aging/payable | Implemented and live-tested
GET /api/v1/organizations/:id/periods | Implemented and live-tested (Sprint 23 — closes the manual period-paste gap)
GET /api/v1/organizations/:id/pos/sales/:id/receipt | Implemented and live-tested (Sprint 25 — real invoice/receipt linked to organization + transaction data, verified via a genuine QR decode round-trip)
GET /api/v1/organizations/:id/sales/invoices/:id/receipt | Implemented and live-tested (Sprint 25)
GET /api/v1/organizations/:id | Implemented and live-tested (Sprint 29)
PATCH /api/v1/organizations/:id/settings | Implemented and live-tested (Sprint 29 — requireShiftForPosSale toggle)
POST /api/v1/organizations/:id/periods | Implemented and live-tested (Sprint 31 — closes the 'only one period ever exists' gap)
/api/v1/zatca/* | Not implemented — blocked on Data Dictionary extraction

## 26_Test_Cases
Test ID | Area | Description | Status
ACC-001 | Accounting | Rejects unbalanced entry (Debit != Credit) | Passing — accounting-posting-engine.spec.ts
ACC-002 | Accounting | Accepts balanced entry, writes correct lines | Passing
ACC-003 | Accounting | Blocks posting into CLOSED period | Passing
ACC-004 | Accounting | Reversal creates counter-entry, does not mutate original | Passing
ACC-005 | Accounting | Refuses double reversal of the same entry | Passing
ACC-006 | Accounting | No duplicate posting under concurrent requests (idempotency) | Planned — needs live Postgres integration test
AUTH-001 | Auth | Issues a token with correct userId/organizationId/roleId on valid login | Passing — auth.service.spec.ts
AUTH-002 | Auth | Rejects wrong password | Passing
AUTH-003 | Auth | Unknown email and wrong password return the identical error (no account enumeration) | Passing
AUTH-004 | Auth | Rejects login into an organization the user doesn't belong to | Passing
AUTH-005 | Auth | Rejects a deactivated user | Passing
TEN-001 | Tenant Isolation | Blocks a request whose path organizationId differs from the token's | Passing — tenant.guard.spec.ts
TEN-002 | Tenant Isolation | Deep repository-level isolation (Prisma extension + Postgres RLS) | Planned — needs live Postgres
RBAC-001 | RBAC | Grants access only when every required permission is present | Passing — permissions.guard.spec.ts
RBAC-002 | RBAC | Blocks and names the missing permission otherwise | Passing
RBAC-003 | RBAC | Cashier role without pos.overrideDiscount is blocked from that action | Passing
AUD-001 | Audit | Only handlers marked @AuditAction produce a log entry | Passing — audit.interceptor.spec.ts
AUD-002 | Audit | Both success and error outcomes are recorded | Passing
ORG-001 | Organizations | Rejects a duplicate VAT number | Passing — organizations.service.spec.ts
ORG-002 | Organizations | Seeds all 13 default roles and hashes the owner's password | Passing
ORG-003 | Organizations | Skips the VAT-uniqueness check (not fails) when no VAT number is given yet | Passing
TB-001 | Accounting (read) | Trial balance sums debit/credit per account and reports balanced when equal | Passing — accounting-query.service.spec.ts
TB-002 | Accounting (read) | Reports isBalanced=false without throwing on a genuinely unbalanced report | Passing
TB-003 | Accounting (read) | 50-line fractional-cents sum has no float drift | Passing
ZQR-001..006 | ZATCA QR | Phase 1/2 TLV encode+decode round-trip, tag ordering, length-overflow and hash-length guards | Passing — qr-encoder.spec.ts
DEF-001 | Accounting HTTP | UnbalancedEntryError maps to HTTP 400 (not a generic 500) via DomainExceptionFilter | Passing — domain-exception.filter.spec.ts; bug found and fixed via live curl smoke test
DEF-002 | Accounting HTTP | ClosedPeriodError maps to HTTP 409 | Passing
DEF-003 | Accounting HTTP | EntryAlreadyReversedError maps to HTTP 409 | Passing
E2E-001 | End-to-end (live server) | Login -> post balanced journal entry -> succeeds with correct lines | Verified live via curl against a running ts-node server (not a unit test)
E2E-002 | End-to-end (live server) | Login -> post unbalanced journal entry -> HTTP 400, and it does NOT appear in the Trial Balance | Verified live via curl
E2E-003 | End-to-end (live server) | Trial Balance reflects only committed entries, isBalanced=true | Verified live via curl
E2E-004 | End-to-end (live server) | Request with a different organizationId in the URL path is blocked (403) | Verified live via curl
E2E-005 | End-to-end (live server) | Request with no bearer token at all is blocked (401) | Verified live via curl
IDEM-001 | Idempotency (band 91) | Replaying the same idempotencyKey returns the ORIGINAL entry, not a duplicate | Passing — accounting-posting-engine.spec.ts
IDEM-002 | Idempotency (band 91) | A different idempotencyKey for the same org still posts a new entry | Passing
IDEM-003 | Idempotency (band 91) | Posting with no key at all never triggers the idempotency path | Passing
E2E-006 | End-to-end (live server) | Same request replayed with the same Idempotency-Key header returns the identical journal entry id; Trial Balance reflects it only once | Verified live via curl
BR-001 | Branches (band 6) | Rejects a duplicate branch code within the same organization | Passing — branches.service.spec.ts
BR-002 | Branches (band 6) | Allows the SAME branch code across two DIFFERENT organizations | Passing
BR-003 | Branches (band 6) | Lists only branches belonging to the requested organization | Passing
E2E-007 | End-to-end (live server) | Create branch succeeds; duplicate code for the same org is rejected live with HTTP 409 | Verified live via curl
E2E-008 | End-to-end (live server) | List branches returns only the created branch | Verified live via curl
SALES-001 | Sales | Computes subtotal/tax/total correctly for a standard-rated line and posts Dr AR / Cr Sales+VAT | Passing — sales.service.spec.ts
SALES-002 | Sales | Omits the VAT line entirely for a zero-rated invoice (no clutter) | Passing
SALES-003 | Sales | Sums multiple lines with mixed tax codes correctly | Passing
SALES-004 | Sales | Rejects an invoice with zero lines | Passing
SALES-005 | Sales | Rejects a line with zero/negative quantity | Passing
SALES-006 | Sales | Rejects an invoice for a customer that doesn't exist in this organization | Passing
SALES-007 | Sales | Passes idempotencyKey straight through to the posting engine | Passing
E2E-009 | End-to-end (live server) | Create customer -> post 2-line mixed-tax invoice -> Subtotal 1200.00, VAT 150.00, Total 1350.00 | Verified live via curl
E2E-010 | End-to-end (live server) | Trial Balance after the invoice shows AR=1350, Sales=1200, VAT=150, isBalanced=true | Verified live via curl
E2E-011 | End-to-end (live server) | Invoicing a nonexistent customer returns HTTP 404 live | Verified live via curl
INV-T-001 | Inventory | Second receipt at a different cost recalculates the weighted average correctly (100@10 + 50@16 -> 12.00) | Passing — inventory.service.spec.ts
INV-T-002 | Inventory | Issuing stock uses the CURRENT weighted average, not the original receipt cost | Passing
INV-T-003 | Inventory | Posts Dr Inventory/Cr Opening Balance Equity on receipt, Dr COGS/Cr Inventory on issue | Passing
INV-T-004 | Inventory | Rejects issuing more than is on hand | Passing
INV-T-005 | Inventory | postJournal=false / postToOpeningBalance=false skips the engine call (integration mode) | Passing
PUR-001 | Purchases | Posts Dr Inventory + VAT Input / Cr Accounts Payable for a stocked line | Passing — purchases.service.spec.ts
PUR-002 | Purchases | Routes a non-stocked line to the general expense account instead of Inventory | Passing
PUR-003 | Purchases | Splits a mixed bill correctly between Inventory and general expense | Passing
PUR-004 | Purchases | Calls InventoryService.receiveStock with postToOpeningBalance=false (no duplicate journal entry) | Passing
POS-T-001 | POS | Cash sale posts Dr Cash / Cr Sales+VAT | Passing — pos.service.spec.ts
POS-T-002 | POS | Mixed payment (band 37) splits correctly between Cash and Card Clearing | Passing
POS-T-003 | POS | Rejects when tender total doesn't match the invoice total | Passing
POS-T-004 | POS | A line with productId triggers a SEPARATE COGS journal entry | Passing
POS-T-005 | POS | Full return reverses BOTH the sale entry and COGS entry, restores stock at ORIGINAL unit cost | Passing
POS-T-006 | POS | Rejects returning a sale that was already returned | Passing
E2E-012 | End-to-end (live server) | Full chain: create product -> purchase 100@10 -> stock=100@10.00 | Verified live via curl
E2E-013 | End-to-end (live server) | POS sell 10@20 STANDARD -> Subtotal 200/VAT 30/Total 230, COGS=100.00, stock=90 | Verified live via curl
E2E-014 | End-to-end (live server) | Trial Balance after purchase+sale balanced across 7 accounts (1480=1480) | Verified live via curl
E2E-015 | End-to-end (live server) | POS return reverses sale+COGS journal entries, stock restored to 100@10.00 exactly | Verified live via curl
E2E-016 | End-to-end (live server) | Trial Balance after return still balanced (self-cancelling reversal lines) | Verified live via curl
E2E-017 | End-to-end (live server) | Attempting to return the same POS sale twice is rejected live with HTTP 400 | Verified live via curl
RPT-001 | Reporting | General Ledger computes a running balance line by line in chronological order | Passing — reporting.service.spec.ts
RPT-002 | Reporting | P&L classifies accounts correctly and nets Sales Returns against Sales | Passing
RPT-003 | Reporting | PROOF: Assets = Liabilities + Equity + Net Income holds for a realistic posted-style trial balance (not an assumed formula) | Passing — concrete mathematical proof, see test comments
RPT-004 | Reporting | Balance Sheet identity still holds with an Opening Balance Equity line present | Passing
E2E-018 | End-to-end (live server) | P&L after purchase+sale scenario: Revenue 200.00, COGS 100.00, Net Income 100.00 | Verified live via curl
E2E-019 | End-to-end (live server) | Balance Sheet after same scenario: Assets 1280.00 = Liabilities 1180.00 + Equity 0.00 + Net Income 100.00 | Verified live via curl
E2E-020 | End-to-end (live server) | General Ledger for the inventory account shows correct running balance (1000.00 -> 900.00) | Verified live via curl
ACC-CH-001 | Chart of Accounts | Rejects a duplicate account code within the same organization | Passing — accounts.service.spec.ts
ACC-CH-002 | Chart of Accounts | Resolves parentCode to the parent's id | Passing
ACC-CH-003 | Chart of Accounts | Rejects creating an account under a parent code that doesn't exist | Passing
ACC-CH-004 | Chart of Accounts | getAccountIdByCode throws a clear setup error when the code is missing | Passing
ACC-CH-005 | Chart of Accounts | seedDefaultChartOfAccounts creates every code from spec band 20's example with correct parent links | Passing
ACC-CH-006 | Chart of Accounts | Account codes are scoped per organization — same code can exist in two different orgs | Passing
E2E-021 | End-to-end (live server) | Default COA seed produces exactly 19 accounts (codes 1000-6100) with correct types and isPostable flags | Verified live via curl
E2E-022 | End-to-end (live server) | Same purchase+sell scenario re-verified AFTER the Chart-of-Accounts refactor: identical financial results (Trial Balance 1480=1480, Net Income 100.00, Balance Sheet balanced), now resolved via real seeded account UUIDs instead of hardcoded strings | Verified live via curl
E2E-023 | End-to-end (live server) | Creating a duplicate account code (1100) is rejected live with HTTP 409 | Verified live via curl
SHIFT-001 | POS Shift | Opens a shift with the given opening cash | Passing — shifts.service.spec.ts
SHIFT-002 | POS Shift | Rejects opening a second shift on a terminal that already has one open | Passing
SHIFT-003 | POS Shift | Allows open shifts on two DIFFERENT terminals simultaneously | Passing
SHIFT-004 | POS Shift | Rejects a negative opening cash amount | Passing
SHIFT-005 | POS Shift | Closing with actual cash matching expected gives zero difference | Passing
SHIFT-006 | POS Shift | Reports a shortage as a negative difference, not silently | Passing
SHIFT-007 | POS Shift | Rejects closing a shift that was already closed | Passing
SHIFT-008 | POS Shift | Rejects closing a shift that doesn't exist | Passing
SHIFT-009 | POS Shift | After closing, a new shift CAN be opened on the same terminal | Passing
E2E-024 | End-to-end (live server) | Trial Balance now shows real account codes/names (e.g. '1300 Inventory') instead of raw UUIDs | Verified live via curl
E2E-025 | End-to-end (live server) | Open shift -> attempt second open on same terminal rejected (400) -> close with a 5.00 SAR shortage computed and reported correctly | Verified live via curl
SHIFT-010 | POS Shift | recordCashMovement accumulates cash sales onto the shift's running total | Passing — shifts.service.spec.ts
SHIFT-011 | POS Shift | recordCashMovement accumulates cash returns onto a separate running total | Passing
SHIFT-012 | POS Shift | A zero cash amount (fully card-paid sale) is a no-op, not an error | Passing
SHIFT-013 | POS Shift | Rejects recording a cash movement against a CLOSED shift | Passing
SHIFT-014 | POS Shift | Rejects recording against a shift that doesn't exist | Passing
SHIFT-015 | POS Shift | End-to-end unit proof: opening 200 + cash sales 115 - cash return 30 = expected 285 at close | Passing
POS-T-007 | POS x Shift integration | Records the cash tender against the open shift after a successful sale | Passing — pos.service.spec.ts
POS-T-008 | POS x Shift integration | Rejects a sale against a shift that isn't OPEN | Passing
POS-T-009 | POS x Shift integration | Rejects a sale against a shift belonging to a DIFFERENT terminal | Passing
POS-T-010 | POS x Shift integration | Rejects a sale referencing a shift that doesn't exist | Passing
POS-T-011 | POS x Shift integration | A return on a sale linked to a still-OPEN shift records a cash return against it | Passing
POS-T-012 | POS x Shift integration | A return on a sale whose shift has since CLOSED still succeeds — shift reconciliation skipped, not blocking | Passing
E2E-026 | End-to-end (live server) | Full shift-linked scenario: open (200) -> sell 115 (total 115) -> sell 50 (total 165) -> return first sale (returns 115) -> close with actual 250 = expected 250, difference 0.00 | Verified live via curl
E2E-027 | End-to-end (live server) | Selling against an already-closed shift is rejected live with HTTP 400 | Verified live via curl
EXP-001..003 | Expenses | Posts Dr Expense+VAT Input/Cr Payment; omits VAT line for zero-rated; rejects non-positive amount | Passing — expenses.service.spec.ts
AST-001..006 | Fixed Assets | Acquisition posting, residual-vs-cost validation, straight-line depreciation calc, accumulation across calls, rejects exceeding depreciable base, rejects unknown asset | Passing — assets.service.spec.ts
BNK-001..003 | Banking | Dr toAccount/Cr fromAccount transfer, rejects non-positive amount, rejects self-transfer | Passing — banking.service.spec.ts
POS-PR-001..005 | POS Partial Return | Prorated tax+COGS on partial return via Sales Returns account, cumulative quantity tracking across multiple partial returns, status transitions to fully RETURNED when exhausted, full returnSale() rejected after any partial, invalid line index rejected | Passing — pos.service.spec.ts
PAY-001..004 | Payments | Customer payment Dr Cash/Cr AR, supplier payment Dr AP/Cr Cash, rejects non-positive amounts, lists filtered by party | Passing — payments.service.spec.ts
STMT-001..003 | Statements | totalInvoiced-totalPaid=balance, fully-paid gives zero balance, no activity gives zero balance and no lines | Passing — statements.service.spec.ts
E2E-028 | End-to-end (live server) | Full 6-module chained scenario: expense (115.00) -> asset acquisition+depreciation (500.00/month) -> bank transfer (500.00) -> invoice+payment+statement (1150/600/550) -> purchase+sell+partial-return (stock 100->90->93) -> FINAL Trial Balance across everything: isBalanced=true, 16444.00=16444.00 | Verified live via curl — single comprehensive run
PAY-APP-001..003 | Sales/Purchases Payment Application | applyPayment updates paidAmount, rejects overpayment, rejects unknown invoice/bill (both Sales and Purchases) | Passing — sales/purchases.service.spec.ts
PAY-APP-004..006 | Payments x Application integration | invoiceId/billId triggers applyPayment with the correct amount; omitting it does not call applyPayment (on-account payment preserved) | Passing — payments.service.spec.ts
E2E-029 | End-to-end (live server) | Invoice 1150.00 -> pay 600 applied to invoice -> attempt +700 rejected live (400, would overpay) -> pay remaining 550 -> final statement balance exactly 0.00 | Verified live via curl
AGE-001..006 | Aging (Receivable/Payable) | Buckets by age (0-30/31-60/61-90/90+), excludes fully-paid invoices, ages on remaining balance not original total, today's invoice = 0 days, empty-state handling, payable mirrors receivable logic | Passing — aging.service.spec.ts
E2E-030 | End-to-end (live server) | Invoice 1150.00 issued today + partial payment 500 -> Receivable Aging shows CURRENT_0_30 bucket with exactly 650.00 outstanding; Payable Aging correctly empty (all-zero buckets, no error) | Verified live via curl
CF-001..003 | Cash Flow Statement | Classifies ASSET_ACQUIRED as investing vs. operating for everything else, bank transfer self-cancels to exactly zero, empty state has no error | Passing — reporting.service.spec.ts
E2E-031 | End-to-end (live server) | Cash sale +230 (operating) + cash expense -115 (operating, net 115.00) + asset acquisition -12000 (investing) + bank transfer 500 (self-cancels to 0) -> net change in cash = -11885.00 exactly | Verified live via curl
UI-001 | Web UI (Sprint 22) | index.html, style.css, and app.js are served with HTTP 200 by the running NestJS server via useStaticAssets | Verified live via curl
UI-002 | Web UI (Sprint 22) | Every API call the UI's JavaScript makes (login, trial-balance, profit-and-loss, create customer with real Arabic text, list accounts) succeeds against the live server exactly as the browser would call it | Verified live via curl simulating the exact fetch() calls in app.js
UI-003 | Web UI (Sprint 23) | New GET /periods endpoint returns the seeded OPEN period, closing the Sprint 22 manual-paste gap | Verified live via curl
UI-004 | Web UI (Sprint 23) | POS screen's exact API call (cash sale) succeeds and returns correct subtotal/tax/total | Verified live via curl
UI-005 | Web UI (Sprint 23) | Assets screen's exact API call (acquire asset) succeeds | Verified live via curl
UI-006 | Web UI (Sprint 23) | Reports screen's three exact API calls (balance-sheet, cash-flow, aging/receivable) all succeed and cross-validate numerically: Balance Sheet 115.00=15.00+0+100.00 (balanced), Cash Flow net change -4885.00 matches the actual cash account balance exactly | Verified live via curl — a genuine cross-module arithmetic proof, not just individually correct responses
UI-007 | Web UI (Sprint 24) | Inventory screen: create product, receive 50 units @ 8.00, check-stock button returns correct quantity and average cost | Verified live via curl
UI-008 | Web UI (Sprint 24) | Purchases screen: create supplier, post a mixed bill (one product-linked line + one unlinked general-expense line) with correct Subtotal/VAT/Total (130.00/19.50/149.50) | Verified live via curl
UI-009 | Web UI (Sprint 24) | Cross-screen integration proof: after the purchase bill, the Inventory screen's stock check shows 60 units at the SAME 8.00 average cost (50 existing + 10 from the bill, both received at identical cost) — not just each screen individually correct, but consistent with each other | Verified live via curl
ORG-001..002 | OrganizationsService.getOrganization (Sprint 25) | Returns the organization row when found, returns null when not found | Passing — organizations.service.spec.ts
RCPT-001..006 | ReceiptsService (Sprint 25) | Composes seller/lines/totals/QR from a real POS sale, correctly describes mixed cash+card payment, 404s on unknown sale, composes an invoice receipt reporting on-account vs partial payment correctly, 404s on unknown invoice | Passing — receipts.service.spec.ts
E2E-032 | End-to-end (live server) — deepest verification in the project | Real POS sale -> GET /receipt returns sellerName pulled from real OrganizationsService data (not hardcoded) -> the returned QR image is decoded via a REAL QR-reading library (pyzbar) and every one of its 5 TLV fields (seller name, VAT number, timestamp, total, VAT) matches the actual transaction data exactly | Verified live via curl + a real QR decode round-trip, not just an individually-correct API response
E2E-033 | End-to-end (live server) | Real unpaid sales invoice (1150.00) -> GET /receipt correctly reports paymentSummary = 'آجل — على الحساب' (on account) | Verified live via curl — the exact call the UI's new 'عرض الفاتورة' button makes
UI-010 | Web UI (Sprint 26) | New Shift screen: open shift, JWT payload decoded client-side to get cashierUserId, close shift with cash reconciliation | Verified live via curl simulating the exact calls, including manual JWT decode matching app.js's decodeJwtPayload()
BUG-001 | Real bug found via live testing (Sprint 26) | Initial Shift screen implementation hardcoded the POS sale's terminalId to 'WEB-UI-01' while the shift-open form defaulted to 'POS-01' — every sale during an open shift would have been rejected by the backend's real terminal-match validation. Caught only by running the actual server end-to-end, not by code review. Fixed by having the sale form use the active shift's own terminalId | Confirmed failing before the fix, confirmed passing after — documented explicitly rather than silently patched
E2E-034 | End-to-end (live server) — cash reconciliation proof | Open shift (200.00) -> cash sale (115.00) linked to shift -> close shift with actualCash=315.00 -> expectedCash=315.00 exactly (200+115), cashDifference=0.00 | Verified live via curl, after the terminal-mismatch fix above
E2E-035 | End-to-end (live server) | POS sale's receipt now shows the REAL soldAt timestamp captured at the moment of sale, not the time the receipt was later requested | Verified live via curl with a 2-second delay between sale and receipt fetch to prove the timestamp doesn't drift
UI-011 | Web UI (Sprint 27) | New Returns screen: search a sale by id, partial return of specific line quantities via return-items, full return via return | Verified live via curl simulating the exact calls
UI-012 | Web UI (Sprint 27) — deliberate business rule verified, not just each call in isolation | After a partial return (2 of 5 units), attempting a FULL return correctly fails with the expected 400 (a documented Sprint 18 design decision, not a newly-discovered limitation); returning the remaining 3 units via return-items instead succeeds and reaches status RETURNED with all remainingQuantities at 0 | Verified live via curl — confirms the UI's full-return button is correctly hidden in this exact scenario rather than assumed correct
ATOM-001 | PurchasesService atomicity fix (Sprint 28) | A bill referencing a non-existent productId is rejected BEFORE any journal entry is posted (calls.length === 0) | Passing — purchases.service.spec.ts
ATOM-002 | PurchasesService atomicity fix (Sprint 28) | A bill with a valid product posts normally with no behavior change | Passing — purchases.service.spec.ts
ATOM-003 | PurchasesService atomicity fix (Sprint 28) | If inventory update fails AFTER the journal entry posts, the entry is automatically reversed via AccountingPostingEngine.reverse() with the correct journalEntryId, then the original error is rethrown | Passing — purchases.service.spec.ts
ATOM-004 | PurchasesService atomicity fix (Sprint 28) | A fully successful bill triggers zero reversal calls | Passing — purchases.service.spec.ts
ATOM-005 | PosService.returnItems atomicity fix (Sprint 28) | If restoring inventory fails after a partial-return journal entry posts, that entry is automatically reversed with the correct id before the error propagates | Passing — pos.service.spec.ts
ATOM-006 | PosService.returnItems atomicity fix (Sprint 28) | A fully successful partial return triggers zero reversal calls | Passing — pos.service.spec.ts
E2E-036 | End-to-end (live server) — the concrete bug, demonstrated and closed | Purchase bill referencing a non-existent productId -> rejected live with 404 -> Trial Balance queried immediately before and after the attempt is IDENTICAL ({totalDebit:0, totalCredit:0}) -> proves no orphan journal entry leaked into the books, closing the exact failure mode described in the Sprint 6-8 gap | Verified live via curl — a before/after ledger-state comparison, not just an error code check
E2E-037 | End-to-end (live server) | Normal purchase bill with a real product still behaves identically to before the fix: stock updates to 5 @ 10.00, journal entry balances exactly (57.50 = 57.50) | Verified live via curl — confirms the fix adds a safety net without changing correct-path behavior
ORG-003..004 | OrganizationsService.updateSettings (Sprint 29) | Updates requireShiftForPosSale and returns the updated row; throws NotFoundException for an unknown organization | Passing — organizations.service.spec.ts
SHIFT-SETTING-001..004 | PosService mandatory-shift setting (Sprint 29) | Rejects a shiftId-less sale when the org requires a shift; allows it when the org doesn't; allows it when NO OrganizationsService is provided at all (backward compatibility); a sale WITH a valid shiftId succeeds even when required | Passing — pos.service.spec.ts — importantly, every pre-existing PosService test in the file continued passing unmodified, proving the optional constructor parameter is truly non-breaking
E2E-038 | End-to-end (live server) — full lifecycle of an opt-in setting | Sale without shift succeeds before opt-in (201) -> PATCH settings enables requireShiftForPosSale -> the same sale request now rejected (400, correct message) -> a sale WITH an open shift succeeds -> PATCH settings disables it again -> shift-less sale succeeds once more | Verified live via curl through all 5 states of the toggle, not just the on/off endpoints in isolation
ZXML-001..021 | ZATCA UBL 2.1 XML generator (Sprint 30) | Each test cites the specific ZATCA business rule ID it verifies (BR-06, BR-13/14/15, BR-16/21/22/24/25/26, BR-45/46/47/48, BR-CO-04, BR-KSA-06/08/09/39/40/37/66/61, BR-KSA-EN16931-01/02), well-formedness via an actual XML parser (not string matching), multi-VAT-category support, XML-escaping of free text, and format validators for VAT number/building number/postal code | Passing — xml-invoice-builder.spec.ts, built directly from the official 'Electronic Invoice XML Implementation Standard v1.2' fetched and read in this session
ZXML-022..025 | ReceiptsService xmlInvoice integration (Sprint 30) | Includes a well-formed xmlInvoice when the organization has full address data; OMITS it (rather than emitting incomplete XML) when address data is missing; correctly maps OUT_OF_SCOPE tax code to ZATCA category 'O'; also generates xmlInvoice for Sales invoice receipts, not just POS | Passing — receipts.service.spec.ts
E2E-039 | End-to-end (live server) — deepest ZATCA verification in the project | Real POS sale with 2 lines (STANDARD + ZERO tax codes) -> GET /receipt -> the returned xmlInvoice validated by an INDEPENDENT XML parser (fast-xml-parser, not the same code that generated it) -> every key field extracted and cross-checked against the actual sale: InvoiceTypeCode=388/name='0200000', real seller name and VAT number (not hardcoded), TaxInclusiveAmount and PayableAmount both exactly 153.50 matching the real sale total, both invoice lines present with correct Arabic text, and the zero-rated line correctly categorized as 'Z' | Verified live via curl + independent XML parsing — a genuine field-by-field cross-check against real transaction data, not just 'the endpoint returned 200'
ZHASH-001 | Independent verification of a spec-stated constant before hardcoding it | The ZATCA spec's documented placeholder for a Previous Invoice Hash (BR-KSA-26, 'first invoice' case) was independently recomputed from scratch (SHA-256 of the character '0', then base64-encoded) via a standalone Python script, and matched the spec's stated value byte-for-byte before being used as a hardcoded constant in the codebase | Verified via bash_tool/python3 in this session — see ZATCA_FIRST_INVOICE_HASH_PLACEHOLDER in xml-invoice-builder.ts
PERIOD-001..006 | PeriodsService.createPeriod (Sprint 31) | Creates an OPEN period when there's no overlap; rejects end<=start; rejects invalid dates; rejects overlap with an existing period for the SAME org; allows a non-overlapping period alongside others; does NOT consider a different organization's periods when checking overlap | Passing — periods.service.spec.ts
E2E-040 | End-to-end (live server) — periods actually usable, not just creatable | New period for 2028 created -> list shows 2 periods -> an overlapping period request correctly rejected (400) -> a REAL POS sale successfully posted using the new period's id as periodId | Verified live via curl — the sale posting step proves the new period is genuinely functional, not just a database row
ZTAX-001..007 | buildTaxInvoiceXml (Sprint 31) | Well-formed XML with buyer block; InvoiceTypeCode name is '0100000' per BR-KSA-06 (vs '0200000' for Simplified); buyer postal address fields present per BR-10/BR-KSA-63; buyer VAT number included per BR-KSA-44 when provided and correctly omitted when not; seller block identical between Simplified and Tax Invoice variants; Simplified variant correctly has NO AccountingCustomerParty block at all | Passing — xml-invoice-builder.spec.ts, each citing the specific business rule it verifies
E2E-041 | End-to-end — Tax Invoice with real buyer data, independently parsed | Full Tax Invoice generated with a complete Saudi buyer (name, 15-digit VAT number, Jeddah address) -> validated by an independent XML parser -> InvoiceTypeCode/name, buyer registration name, buyer VAT number, and buyer city all extracted and confirmed correct -> TaxInclusiveAmount matches the input total exactly (1150.00) | Verified via ts-node script + fast-xml-parser in this session
POS-001 | POS | Cash sale posts correct Dr Cash / Cr Sales+VAT | Planned — needs POS module
INV-001 | Invoice | Standard invoice snapshot unaffected by later customer edits | Planned — needs Invoice module

## 27_ZATCA_Test_Cases
Test ID | Description | Status
ZATCA-001 | Simplified invoice QR decodes to correct seller/VAT/timestamp/total/VAT-total | BLOCKED — needs official Data Dictionary + Security Features doc first
ZATCA-002 | Standard invoice validates against official XML Schema | BLOCKED
ZATCA-003 | Standard invoice validates against official Schematron/business rules | BLOCKED
ZATCA-004 | Rejected invoice is not silently retried indefinitely (non-retryable vs retryable) | BLOCKED
ZATCA-005 | Duplicate submission is idempotent (no duplicate financial transaction) | BLOCKED

## 28_Deployment_Checklist
Item | Status
Docker image for API | Not started
Docker image for Web | Not started
Environment variable / secrets management | Not started
Database migration pipeline (prisma migrate deploy) | Not started
Health check endpoint | Not started
Backup schedule + restore test | Not started

## 29_Compliance_Checklist
Item | Status
ZATCA_SOURCES.md created with verifiable official links | Done
Data Dictionary downloaded + version logged | Link verified (20230519_EInvoice_Data_Dictionary vF.xlsx); content not yet extracted — xlsx text extraction not available in this session
XML Implementation Standard downloaded + content verified | Done — v1.2, 2023-05-19, full 72-page text fetched and reviewed
Security Features Implementation Standards downloaded + content verified | Done — v1.2, 2023-05-19, full 27-page text fetched and reviewed
QR TLV encoder implemented against verified spec, with tests | Done — apps/api/src/modules/zatca/qr-encoder.ts (+.spec.ts)
XML mapper / UBL generator / CSR-CSID services implemented | Not started — requires Data Dictionary content first per ZATCA_SOURCES.md §4
Debit=Credit invariant enforced in code with tests | Done
Immutable posted journal entries (reversal-only correction) | Done
Closed-period posting blocked | Done
Tenant isolation enforced + tested | Path-level isolation (TenantGuard) done, tested, and live-verified via curl (403 on cross-tenant path); deep repository-level isolation (Prisma extension + Postgres RLS) still pending real DB
Live server runs and responds correctly end-to-end | Done — app.module.ts + main.ts booted via ts-node; login, posting, Trial Balance, tenant isolation, and auth-required all verified live via curl this session

## 30_Risk_Register
Risk | Impact | Mitigation
Coding ZATCA XML/QR from memory or unofficial libraries | Legal/compliance failure, rejected submissions | Hard block in place — see docs/GAP_ANALYSIS.md item 1; ZATCA module not started
Operational modules (POS/Sales) built before Accounting Core is stable | Ledger corruption, unrecoverable financial errors | Sequenced roadmap in docs/MVP_ROADMAP.md prevents this
Tenant data leakage across organizations | Severe security/legal risk | Planned dual-layer isolation (app-level guard + Postgres RLS) — not yet implemented
Using FLOAT/DOUBLE for money | Silent rounding errors in financial statements | Schema uses Prisma Decimal(18,4) throughout — verified in schema.prisma
Purchases-to-Inventory and POS-Return-to-Inventory are two separate calls, not one atomic transaction | A crash between the two could leave a posted bill/reversal whose stock quantity wasn't updated | MOSTLY CLOSED in Sprint 28-29 — pre-validation + compensating reversal now cover PurchasesService.createBill() and PosService.returnItems() (demonstrated live: a bill with a bad productId used to post a bad GL entry, now rejected with zero ledger impact). PosService.returnSale() was explicitly reviewed in Sprint 29 and found NOT to need the same fix — its productId always comes from the sale's own internally-generated inventoryEffects, never user input on the return request, so the specific failure mode this pattern closes cannot occur there. True DB-level atomicity still needs real Prisma/Postgres $transaction, still blocked in this sandbox
Whether a shift should be mandatory for every POS sale was an open product decision since Sprint 12 | POS sales could be made with no shift tracking at all, with no way for a business to require otherwise | CLOSED in Sprint 29 — resolved as a per-organization opt-in setting (requireShiftForPosSale, default false) rather than a single hardcoded answer, since different business types legitimately want different defaults. Backward compatible by construction: OrganizationsService is an optional trailing constructor parameter on PosService, so no existing call site or test needed to change
Zero User Interface exists after 21 sprints of backend work | Spec band 143 explicitly requires a modern commercial UI (RTL-first, clean sidebar, quick-create, etc.) — every deliverable so far is an API endpoint, not a usable product for a non-technical user | CLOSED across Sprint 22-27 — the UI now covers every core operational module: login, dashboard, sales, POS, customers, inventory, purchases, fixed assets, reports, chart of accounts, shift management, and returns, all live-verified including cross-screen integration tests and a real bug caught and fixed via live testing (Sprint 26). Still explicitly NOT the final Next.js app from ARCHITECTURE.md — this is a lightweight bootstrap UI, not the polished commercial product the full spec envisions

## 31_MVP_Roadmap
Phase | Status
0. Repository Audit | Done
1. Official ZATCA Research | Mostly done — XML Implementation Standard v1.2 and Security Features v1.2 (both 2023-05-19) fully fetched and mapped; only the Data Dictionary XLSX content remains unextracted
2. Product Blueprint | Done
3. Database & ERD (first layer) | Done — plus a real AccountsService (Chart of Accounts CRUD + default-COA seeder) implemented and live-tested in Sprint 10
4. Security Foundation | Core logic + Branches CRUD done and tested (23 tests) AND live-wired: a real running NestJS server (app.module.ts + main.ts) verified end-to-end via curl (login, tenant isolation 403, missing-token 401, duplicate branch code 409) — only a real Postgres/Prisma backing (currently in-memory) remains
5. Accounting Core | Posting engine (incl. idempotency) + Trial Balance + HTTP controller done, tested (23 tests incl. DomainExceptionFilter + idempotency), AND live-verified via curl: balanced entry posts correctly, unbalanced entry rejected with HTTP 400, replayed idempotency key returns the same entry (no duplicate), Trial Balance correct
6-9. Sales/Purchases/Inventory/POS/Reporting | Sales, Purchases, Inventory (Weighted Average), POS (Sell+Full/Partial Return+Shift integration), Reporting (GL/P&L/Balance Sheet), a real Chart of Accounts, PLUS Expenses, Fixed Assets, Banking, Payments, and Statements (Sprint 13-18) — all done and live-verified TOGETHER in one chained 6-step scenario ending in a fully balanced Trial Balance (16444.00=16444.00) across every module. Documented gaps: Purchases/POS-Return-to-Inventory still two separate calls not one transaction; mandatory-shift policy still an open decision; Statements is invoiced-minus-paid only, not a full aged ledger with payment application
10. Invoice Engine | Not started — Sales/Purchases/POS currently post minimal ad-hoc records, not the full Canonical Invoice Model (bands 60-84)
11. ZATCA | QR encoder done and tested (6 tests) against verified official spec — XML Mapper/CSR/CSID blocked pending Data Dictionary extraction
12. Industry Packs | Not started
13. Hardening | Not started
14. Deployment | Not started